## Task Estimates
OpenAssess: PERT Task Breakdown and Effort Estimate
Estimates are in working days for one full-time developer and cover the P0 scope (authentication, assessments, MCQ and coding questions, timed attempts, evaluation, results). Admin dashboard, notifications, analytics and anti-cheating are excluded. Blue cells are inputs; black cells are formulas.
ID | Phase | Task | Optimistic (days) | Most likely (days) | Pessimistic (days) | Expected (days) | Std dev (days) | Variance (days²)
1.1 | Phase 1: Foundation | Repository setup, branching rules, license and README skeleton | 0.5 | 1 | 2 | 1.0833 | 0.25 | 0.0625
1.2 | Phase 1: Foundation | Docker Compose for FastAPI, PostgreSQL and Redis | 1 | 2 | 4 | 2.1667 | 0.5 | 0.25
1.3 | Phase 1: Foundation | FastAPI project skeleton and configuration management | 1 | 2 | 3 | 2 | 0.33333 | 0.11111
1.4 | Phase 1: Foundation | SQLAlchemy session and Alembic migration setup | 1 | 2 | 4 | 2.1667 | 0.5 | 0.25
1.5 | Phase 1: Foundation | GitHub Actions pipeline (lint and pytest) | 1 | 2 | 4 | 2.1667 | 0.5 | 0.25
1.6 | Phase 1: Foundation | React, TypeScript and Tailwind scaffold | 1 | 2 | 3 | 2 | 0.33333 | 0.11111
2.1 | Phase 2: Authentication | User model and migration | 0.5 | 1 | 2 | 1.0833 | 0.25 | 0.0625
2.2 | Phase 2: Authentication | Registration and login with password hashing and JWT | 2 | 3 | 5 | 3.1667 | 0.5 | 0.25
2.3 | Phase 2: Authentication | Role-based access control (admin, creator, candidate) | 2 | 3 | 5 | 3.1667 | 0.5 | 0.25
2.4 | Phase 2: Authentication | Token expiry, refresh and logout | 1 | 2 | 3 | 2 | 0.33333 | 0.11111
2.5 | Phase 2: Authentication | Authentication tests | 1 | 2 | 3 | 2 | 0.33333 | 0.11111
2.6 | Phase 2: Authentication | Login and registration UI with route guards | 2 | 3 | 5 | 3.1667 | 0.5 | 0.25
3.1 | Phase 3: Assessments | Assessment, question and test case models and migrations | 2 | 3 | 5 | 3.1667 | 0.5 | 0.25
3.2 | Phase 3: Assessments | Assessment CRUD API with publish and archive | 2 | 3 | 5 | 3.1667 | 0.5 | 0.25
3.3 | Phase 3: Assessments | Question API for MCQ and coding questions with test cases | 3 | 4 | 7 | 4.3333 | 0.66667 | 0.44444
3.4 | Phase 3: Assessments | Resource-level authorization and hidden test case protection | 1 | 2 | 4 | 2.1667 | 0.5 | 0.25
3.5 | Phase 3: Assessments | Creator UI: assessment list and creation | 3 | 5 | 8 | 5.1667 | 0.83333 | 0.69444
3.6 | Phase 3: Assessments | Creator UI: question editor with Monaco | 4 | 6 | 10 | 6.3333 | 1 | 1
3.7 | Phase 3: Assessments | Assessment and question tests | 2 | 3 | 4 | 3 | 0.33333 | 0.11111
4.1 | Phase 4: Candidate Workflow | Attempt model and start endpoint (schedule and attempt limit checks) | 2 | 3 | 5 | 3.1667 | 0.5 | 0.25
4.2 | Phase 4: Candidate Workflow | Server-side timer enforcement and auto-submit | 2 | 4 | 7 | 4.1667 | 0.83333 | 0.69444
4.3 | Phase 4: Candidate Workflow | Answer submission API (save and update answers) | 2 | 3 | 5 | 3.1667 | 0.5 | 0.25
4.4 | Phase 4: Candidate Workflow | Candidate UI: assessment list and instructions | 2 | 3 | 4 | 3 | 0.33333 | 0.11111
4.5 | Phase 4: Candidate Workflow | Candidate UI: test-taking screen with timer and MCQ navigation | 4 | 6 | 9 | 6.1667 | 0.83333 | 0.69444
4.6 | Phase 4: Candidate Workflow | Candidate UI: coding editor with run and submit | 3 | 5 | 8 | 5.1667 | 0.83333 | 0.69444
4.7 | Phase 4: Candidate Workflow | Candidate workflow tests | 2 | 3 | 5 | 3.1667 | 0.5 | 0.25
5.1 | Phase 5: Evaluation | MCQ scoring engine | 1 | 2 | 3 | 2 | 0.33333 | 0.11111
5.2 | Phase 5: Evaluation | Deploy and configure Judge0 | 1 | 3 | 6 | 3.1667 | 0.83333 | 0.69444
5.3 | Phase 5: Evaluation | Code execution service client | 3 | 4 | 7 | 4.3333 | 0.66667 | 0.44444
5.4 | Phase 5: Evaluation | Asynchronous evaluation with Celery and Redis, status endpoint | 3 | 5 | 8 | 5.1667 | 0.83333 | 0.69444
5.5 | Phase 5: Evaluation | Test-case evaluation, partial scoring and result mapping | 2 | 4 | 7 | 4.1667 | 0.83333 | 0.69444
5.6 | Phase 5: Evaluation | Execution limits, error handling and retries | 2 | 3 | 5 | 3.1667 | 0.5 | 0.25
5.7 | Phase 5: Evaluation | Evaluation tests (mocked and integration) | 2 | 4 | 6 | 4 | 0.66667 | 0.44444
6.1 | Phase 6: Results | Score aggregation and result model | 1 | 2 | 4 | 2.1667 | 0.5 | 0.25
6.2 | Phase 6: Results | Results API for candidates and creators | 2 | 3 | 5 | 3.1667 | 0.5 | 0.25
6.3 | Phase 6: Results | Candidate result UI | 2 | 3 | 5 | 3.1667 | 0.5 | 0.25
6.4 | Phase 6: Results | Creator reports and CSV export | 3 | 5 | 8 | 5.1667 | 0.83333 | 0.69444
6.5 | Phase 6: Results | Results tests | 1 | 2 | 3 | 2 | 0.33333 | 0.11111
7.1 | Phase 7: Quality | Security review and authorization audit | 2 | 3 | 5 | 3.1667 | 0.5 | 0.25
7.2 | Phase 7: Quality | Rate limiting and input validation hardening | 1 | 2 | 4 | 2.1667 | 0.5 | 0.25
7.3 | Phase 7: Quality | Audit logging | 1 | 2 | 3 | 2 | 0.33333 | 0.11111
7.4 | Phase 7: Quality | Test coverage improvements and end-to-end smoke tests | 3 | 4 | 7 | 4.3333 | 0.66667 | 0.44444
7.5 | Phase 7: Quality | OpenAPI documentation cleanup | 1 | 2 | 3 | 2 | 0.33333 | 0.11111
7.6 | Phase 7: Quality | Load check on the submission path | 1 | 2 | 4 | 2.1667 | 0.5 | 0.25
8.1 | Phase 8: Open-Source Release | CONTRIBUTING, CODE_OF_CONDUCT, SECURITY and issue and PR templates | 1 | 1.5 | 3 | 1.6667 | 0.33333 | 0.11111
8.2 | Phase 8: Open-Source Release | Setup, architecture and API documentation | 2 | 3 | 5 | 3.1667 | 0.5 | 0.25
8.3 | Phase 8: Open-Source Release | Production deployment guide and compose file | 1 | 2 | 4 | 2.1667 | 0.5 | 0.25
8.4 | Phase 8: Open-Source Release | Seed data and demo environment | 1 | 1.5 | 3 | 1.6667 | 0.33333 | 0.11111
8.5 | Phase 8: Open-Source Release | Version tag and changelog for v0.1 | 0.5 | 1 | 2 | 1.0833 | 0.25 | 0.0625

## Summary
OpenAssess: Estimate Summary
Totals are calculated from the Task Estimates tab. Blue cells are assumptions you can change.
Assumptions
Working days per week | 5
Z-score for 68% range | 1
Z-score for 95% range | 1.96
Phase | Tasks | Optimistic (days) | Most likely (days) | Pessimistic (days) | Expected (days) | Variance (days²) | Std dev (days) | Expected (weeks)
Phase 1: Foundation | 6 | 5.5 | 11 | 20 | 11.5833 | 1.0347 | 1.0172 | 2.3167
Phase 2: Authentication | 6 | 8.5 | 14 | 23 | 14.5833 | 1.0347 | 1.0172 | 2.9167
Phase 3: Assessments | 7 | 17 | 26 | 43 | 27.3333 | 3 | 1.7321 | 5.4667
Phase 4: Candidate Workflow | 7 | 17 | 27 | 43 | 28 | 2.9444 | 1.7159 | 5.6
Phase 5: Evaluation | 7 | 14 | 25 | 42 | 26 | 3.3333 | 1.8257 | 5.2
Phase 6: Results | 5 | 9 | 15 | 25 | 15.6667 | 1.5556 | 1.2472 | 3.1333
Phase 7: Quality | 6 | 9 | 15 | 26 | 15.8333 | 1.4167 | 1.1902 | 3.1667
Phase 8: Open-Source Release | 5 | 5.5 | 9 | 17 | 9.75 | 0.78472 | 0.88585 | 1.95
Total | 49 | 85.5 | 142 | 239 | 148.75 | 15.1042 | 3.8864 | 29.75
Project estimate | Days | Weeks
Expected duration | 148.75 | 29.75
Standard deviation | 3.8864 | 0.77728
68% range, low | 144.8636 | 28.9727
68% range, high | 152.6364 | 30.5273
95% range, low | 141.1326 | 28.2265
95% range, high | 156.3674 | 31.2735
Project standard deviation is the square root of the summed task variances, not the sum of the task standard deviations.